## Working route
Blackboard Group No ?? Class XYY | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | PM class date | =====> | 2022-05-02 | Sunday May.1 |  |  | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | -9 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2022-04-23 | PM class plus | 0 | days
Each group member | Project Mgmt Activity | share with Group |  | Monday July.25 (4 pm) | TO DO
Group Meeting Agenda ==> | create MS Teams Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to group members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 hrs (2pm) | Tuesday July.26 (6.30 pm) | TO DO | review progress, refine plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. |  |  | TO DO | Group decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Friday Apr.22 | TO DO | Group decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Wednesday Apr.20 | TO DO | Submit final version of artefacts from Teams to Blackboard. Backup Teams files. | updated DONE items below with actual hours. |  | Wednesday Apr.20 | TO DO
| request review from professor | Group's Team Channel > Files > click ..._Plan.xlsx > click Conversation (top right) > @your_professor "Please review." |  | Thursday July.28 (10 pm) |  | request review from professor | Group's Team Channel > Files > click filename > click Conversation (top right) > @your_professor "Please review." |  |  |  | request review from professor | Group's Team Channel > Files > click filename > click Conversation (top right) > @your_professor "Please review." |  | Friday May.13 |  | request review from professor | Group's Team Channel > Files > click filename > click Conversation (top right) > @your_professor "Please review." |  | Wednesday Apr.20
[Aynur Gulkanat] Fundamentals | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | Information acquired and decided to deliver our tasks on Monday, with Whatsapp (since everyone uses and are available on Whatsapp). | 2 hrs (8pm) | Monday August.1 (9 pm) | Complete the individual part | All the information was improvised and got all the things ready for testing on Tuesday August.2 | Getting things ready for submission and displayed among group members to get the things correct, if something was found faulty. | 5.3 hrs (10 am) | Sunday August.6 (10 am) |  |  |  |  | Saturday May.14 |  |  |  |  | Thursday Apr.21 |  |  |  |  | Thursday Apr.21
[Jenil Shah] Manipulations | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | Talked with the team members about work distribution and started meeting to interact. Made a decision on what to do and which part should be done later. | 2 hrs (4pm) | Monday August.1 (6 pm) | Complete the individual part | Finish Version 1, proceeded with the testing, wrote down the results and finalizing Version1. | Delivery criteria was agreed on that the files should work together with no errors, and that there are no missing files. | 6 hrs (7.45 am) | Sunday August.6 (7.45 am) |  |  |  |  | Saturday May.14 |  |  |  |  | Thursday Apr.21 |  |  |  |  | Thursday Apr.21
[Prashansa] Tokenizing | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | Information acquired and decided to execute all the things on MONDAY, itself and scheduled the group meeting on the Whatsapp (since everyone was available on the Whatsapp) | 2 hrs (5.49 pm) | Monday August.1 (10 pm) | Complete the individual part | Complete my part of the work and tested it and checked that if it's working properly. | We agreed on completed work, with the comments, that our work is working fine and nothing was missing. | 5 hrs (1 pm) | Sunday August.6 (1 pm) |  |  |  |  | Saturday May.14 |  |  |  |  | Thursday Apr.21 |  |  |  |  | Thursday Apr.21
[Dev Soni] Conversions Group Leader | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | Made the bb06 group for the final project submissions and along with all other members of the group, distributed the work equally. Everyone were came up with what they wanted to do actually and we all agreed upon it and started executing the work, for the project. | 2 hrs (10 pm) | Tuesday August.2 (8.36 pm) | Complete the individual part and take a check, if anyone from the team needs my help | Checked everyone's work and made sure that they were up to the mark. | I created the main file and took a final meeting before getting, things ready for the submission. | 6 hrs (9 pm) | Sunday August.6 (9 pm) |  |  |  |  | Sunday May.15 |  |  |  |  | Friday Apr.22 |  |  |  |  | Friday Apr.22
|  |  |  | milestone |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | DUE DATE upload to Blackboard |  |  |  |  | ABSOLUTE DEADLINE
[7 empty] | What is the group's criteria for acceptance of development (individual files) when promoted to integration (Teams group Files) -- remember the SDLC and Version Control flow? What is definition of done / good enough? Who decides that? | Our acceptance of individual files, is that all the criterias should match with the instructions that has been provided to us, so far for the project. We work while keeping in mind about the SDLC process! Executing all the works in order, step-by-step with requirements to coding to testing the code and at last uploading the final code or Version for grading. Group Leader (Dev Soni) decides all of that. | [10 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.